## 目录
Tiandubang （jiaxing）Metal Technology Co., Ltd.
New Product Development APQP
| Project name | Design and development of Car support
| Project number | TDB-220514
PMC
| Customer Name | EBM
| Model number | / | Technology
Technology
| Product name | Bracket | PMC
Technology
| Product part number | 8317080431 | Project leader
project team
| Product drawing number | 8317080431 | project team
project team
| Project start time： | 2022-05-10 | Project leader
| Contract review time ： | 2022-05-14
| Pilot production time： | 2022-06-07
| PPAP Submission Time： | 2022-06-18
| Mass-produced time： | 2022-08-20

## APQP开发计划
Tiandubang （jiaxing）Metal Technology Co., Ltd.
New project APQP development plan
Customer Name ： |  |  | EBM |  | Project name： |  |  |  |  | Contract review time： | [5 empty] | 2022-05-14 | [13 empty] | NO.JL-104
Product description： |  |  | Bracket |  | Start Time ： |  |  |  |  | PPAP DATE： |  |  |  |  | 2022-06-18 | [14 empty] | Pre-production date： | [5 empty] | 2022-06-07
NO |  | Planning steps and contents |  | File or record | Responsible department | plan |  | actual |  | status | 2022-05-01 | [10 empty] | 2022-06-01 | [9 empty] | 2022/7月
[6 empty] | start | finish | start | finish |  | 2022-01-01 | 2022-01-04 | 2022-01-07 | 2022-01-10 | 2022-01-13 | 2022-01-16 | 2022-01-19 | 2022-01-22 | 2022-01-25 | 2022-01-28 | 2022-01-31 | 2022-02-01 | 2022-02-04 | 2022-02-07 | 2022-02-10 | 2022-02-13 | 2022-02-16 | 2022-02-19 | 2022-02-22 | 2022-02-25 | 2022-02-28 | 2022-03-01 | 2022-03-04 | 2022-03-07 | 2022-03-10 | 2022-03-13 | 2022-03-16 | 2022-03-19 | 2022-03-22 | 2022-03-25 | 2022-03-28 | 2022-03-31
Phase 1: Plan and define the project phase
1 | 1.1 | Customer request input |  | New project development application form | PMC | 2023-05-10 | 2023-05-11 | 2023-05-10 | 2023-05-11 | done | bar: 2022-01-10
Customer requirements/sample/technical requirements | bar: 2022-01-10
External document review form | bar: 2022-01-10
|  |  |  | Project feasibility analysis report | Technology |  |  |  |  | 完成 | bar: 2022-01-10
| 1.2 | Accounting and quotation |  | Product quotations | Technology | 2023-05-14 | 2023-05-15 | 2023-05-14 | 2023-05-15 | done | bar: 2022-01-16
| 1.3 | contract review |  | Contract review form | PMC | 2023-05-14 | 2023-05-15 | 2023-05-14 | 2023-05-15 | done | bar: 2022-01-16
| 1.4 | Approval and formal project approval |  | New product development application/project approval report | Technology | 2023-05-14 | 2023-05-15 | 2023-05-14 | 2023-05-15 | done | bar: 2022-01-16
| 1.5 | Set up project team |  | Project team members and responsibility sheet | Project leader | 2023-05-15 | 2023-05-15 | 2023-05-15 | 2023-05-15 | done | bar: 2022-01-16
| 1.6 | APQP progress plan |  | APQP development plan | project team | 2022-05-16 | 2022-05-18 | 2022-05-16 | 2024-05-18 | done | bar: 2022-01-19
| 1.7 | Determine design objectives/reliability/quality objectives |  | Reliability and quality objectives and standard analysis, environmental requirements | project team | 2022-05-19 | 2022-05-20 | 2022-05-19 | 2022-05-20 | done | bar: 2022-01-19
| 1.8 | Three initial document formulation |  | Initial bill of materials | project team | 2022-05-21 | 2022-05-22 | 2022-05-21 | 2022-05-22 | done | bar: 2022-01-22
Preliminary Process Flow Chart | bar: 2022-01-22
Initial list of special features | bar: 2022-01-22
| 1.9 | Prepare product assurance plan |  | Product assurance plan | Project leader | 2022-05-23 | 2022-05-25 | 2022-05-23 | 2022-05-25 | done | bar: 2022-01-25
| 1.10 | Management support/review record |  | Review record 1 | General Manager | 2022-05-26 | 2022-05-26 | 2022-05-26 | 2022-05-26 | done | bar: 2022-01-25
Phase 2:product design, development and verification
2 | 2.1 | Product design input |  | Customer requirements/sample/technical requirements | Technology department | 2022-05-27 | 2024-05-28 | 2022-05-27 | 2024-05-28 | done | bar: 2022-01-28
New product development and design objectives | bar: 2022-01-28
| 2.2 | 设计验证计划 |  | 设计验证计划（DVP） | 技术部 | 2022-01-21 | 2022-01-22 | 2022-01-21 | 2022-01-22 | 完成 | bar: 2022-01-22
| 2.3 | Prepare sample control plan |  | Sample control plan | project team | 2022-05-29 | 2022-05-30 | 2022-05-29 | 2022-05-30 | done | bar: 2022-01-28
| 2.4 | Determine the delivery date of the sample |  | Sample delivery schedule | project team | 2022-05-31 | 2022-06-01 | 2022-05-31 | 2022-06-01 | done | bar: 2022-02-01
| 2.5 | Design and development input Review Verification (1) |  | Design review/validation record | project team | 2022-06-02 | 2022-06-06 | 2022-06-02 | 2022-06-06 | done | bar: 2022-02-04
| 2.6 | Sample confirmation |  | Sample confirmation record form | project team | 2022-06-09 | 2022-06-17 | 2022-06-13 | 2022-06-18 | done | bar: 2022-02-16
| 2.7 | Design confirmation |  | A-2 Check list | project team | 2022-05-20 | 2022-05-25 | 2022-05-20 | 2022-05-25 | done | bar: 2022-01-25
Materials List | bar: 2022-01-25
Product and process specific characteristics | bar: 2022-01-25
Equipment/tooling/measuring tools and test equipment list | bar: 2022-01-25
A-3 Check list | bar: 2022-01-25
| 2.8 | Stage review/Manager support |  | A-2 Check list | General Manager | 2022-05-26 | 2022-05-27 | 2022-05-26 | 2022-05-27 | done | bar: 2022-01-28
Review record 2 | bar: 2022-01-28
Group feasibility commitment | bar: 2022-01-28
Phase 3: Process design and development
3 | 3.1 | Review of process design and development inputs(二） |  | Design review/validation record | project team | 2022-06-02 | 2022-06-06 | 2022-06-02 | 2022-06-06 | done | bar: 2022-01-28
| 3.2 | Packaging standard |  | Product packaging specification | project team | 2022-06-06 | 2022-06-06 | 2022-06-06 | 2022-06-06 | done | bar: 2022-02-07
| 3.3 | Product/process quality system review(三） |  | Design review/validation record | project team | 2022-06-15 | 2022-06-19 | 2022-06-15 | 2022-06-19 | done | bar: 2022-02-19
|  |  |  | A-4 Check list | project team |  |  |  |  | done | bar: 2022-02-19
| 3.4 | Process charting |  | Process flow chart | Technology department | 2022-06-15 | 2022-06-19 | 2022-06-15 | 2022-06-19 | done | bar: 2022-02-19
A-6 Check list | bar: 2022-02-19
| 3.5 | Production line planning |  | Site layout plan | Production Department | 2022-06-15 | 2022-06-19 | 2022-06-15 | 2022-06-19 | done | bar: 2022-02-19
A-5 Check list | bar: 2022-02-19
| 3.6 | PFMEA Analysis |  | PFMEA | Technology department | 2022-06-15 | 2022-06-19 | 2022-06-15 | 2022-06-19 | done | bar: 2022-02-19
A-7 Check list | bar: 2022-02-19
| 3.7 | Prepare pilot production control plan |  | Pilot production control plan | Technology department | 2022-06-15 | 2022-06-19 | 2022-06-15 | 2022-06-19 | done | bar: 2022-02-19
A-8 Checklist | bar: 2022-02-19
| 3.8 | Validation of tooling, process equipment and measuring equipment |  | List of tools and process equipment | Production Department | 2022-06-15 | 2022-06-19 | 2022-06-15 | 2022-06-19 | done | bar: 2022-02-19
Equipment capacity measurement chart | bar: 2022-02-19
| 3.9 | Measuring and experimental equipment |  | List of monitoring and measuring equipment | Technology department | 2022-06-15 | 2022-06-19 | 2022-06-15 | 2022-06-19 | done | bar: 2022-02-19
MSA Analysis plan | bar: 2022-02-19
SPC Analysis plan | bar: 2022-02-19
| 3.10 | Prepare process work instructions |  | Operation instruction | Technology department | 2022-06-18 | 2022-06-19 | 2022-06-18 | 2022-06-19 | done | bar: 2022-02-19
| 3.11 | Prepare production process validation plan |  | Production process validation plan | project team | 2022-06-18 | 2022-06-19 | 2022-06-18 | 2022-06-19 | done | bar: 2022-02-19
| 3.12 | Prepare packing instructions |  | Product packaging specification | Technology department | 2022-06-18 | 2022-06-19 | 2022-06-18 | 2022-06-19 | done | bar: 2022-02-19
| 3.13 | Design Review/Verification (4) |  | Product packaging specification | project team | 2022-06-20 | 2022-06-22 | 2022-06-20 | 2022-06-22 | done | bar: 2022-02-22
| 3.14 | Stage review/Manager support |  | Review record 3 | General Manager | 2022-06-22 | 2022-06-25 | 2022/622 | 2022-06-25 | done | bar: 2022-02-25
Phase 4: product and process validation
4 | 4.1 | Initial production |  | Pilot production plan | Production Department | 2022-06-28 | 2022-06-28 | 2022-06-28 | 2022-06-28 | done | bar: 2022-02-28
| 4.2 | PPAP Product pilot production PPAP Document preparation |  | Trial production record, trial production appraisal | Production Department Technology department | 2022-06-10 | 2022-06-15 | 2022-06-09 | 2022-06-13 | done | bar: 2022-03-13
| 4.3 | Measurement systems analysis |  | MSA Analysis report | Technology department | 2022-03-10 | 2022-03-15 | 2022-03-10 | 2022-03-15 | done | bar: 2022-03-13
| 4.4 | Initial process study |  | Initial capability study report | Technology department | 2022-03-10 | 2022-03-15 | 2022-03-10 | 2022-03-15 | done | bar: 2022-03-13
| 4.5 | Product and production confirmation |  | Dimensional inspection report | Quality Department | 2022-03-13 | 2022-03-15 | 2022-03-13 | 2022-03-15 | done | bar: 2022-03-16
|  |  |  | Material test report |  | 2022-03-13 | 2022-03-20 | 2022-03-13 | 2022-03-20 | bar: 2022-03-22
|  |  |  | Performance test report |  | 2022-03-13 | 2022-03-22 | 2022-03-13 | 2022-03-22 | bar: 2022-03-22
| 4.6 | Carry out package evaluation |  | Package evaluation report | project team | 2022-03-15 | 2022-03-18 | 2022-03-15 | 2022-03-18 | done | bar: 2022-03-22
| 4.7 | PPAP Submission |  | PPAP Document | PMC | 2022-03-15 | 2022-03-18 | 2022-03-15 | 2022-03-18 | done | bar: 2022-03-22
| 4.8 | Production validation test |  | Test report | Technology department | 2022-03-15 | 2022-03-22 | 2022-03-15 | 2022-03-22 | done | bar: 2022-03-22
|  |  |  | PSW approved by customer | Customer | 2022-03-20 | 2022-03-22 | 2022-03-20 | 2022-03-22 | done | bar: 2022-03-22
| 4.9 | Develop production control plan |  | Production control plan | Technology department | 2022-03-18 | 2022-03-22 | 2022-03-18 | 2022-03-22 | done | bar: 2022-03-22
A-8 Control plan Checklist | bar: 2022-03-22
| 4.10 | Planning approval/management support |  | Product quality planning summary and certification | General Manager | 2022-03-18 | 2022-03-22 | 2022-03-18 | 2022-03-22 | done | bar: 2022-03-22
Project phase review Table 4 | bar: 2022-03-22
Phase 5：Feedback, evaluation and corrective action
5 | 5.1 | start production |  | According to customer's order requirements | Team | 2022-03-25 |  | 2022-03-25
| 5.3 | Customer satisfaction |  | Customer satisfaction evaluation form complaint report | PMC
| 5.2 | Reduced Variation |  | X-R control chart | QC | 2022-03-20 | 2022-03-25 | 2022-03-20 | 2022-03-25 | done | bar: 2022-03-25
| 5.4 | Delivery and service |  | Deliver performance statistics service reports | PMC
| 5.5 | Continuous improvement |  | Dynamic PFMEA necessary improvement program | Project group
Remarks
Formulate： |  | Lei Zhou |  |  | Audit： |  |  | Authorization： |  |  | 2022-01-10: #REF!

## 1.5 成立项目小组
Tiandubang （jiaxing）Metal Technology Co., Ltd. | [6 empty] | 返回
APQP
JL-103
Project name |  | Design and development of Car support |  | Project number | TDB-220514
NO | Members name | Department | Duty | Project development responsibility statement |  | TEL
1 | Lei Zhou | Technology | Technology Manager | Lead the development of new products and propose the necessary resources to ensure the project development |  | 18816906186
2 | Lei FU | PMC | PMC Manager | Collect customer requirements, customer feedback and information transfer, responsible for material and single product procurement, responsible for warehouse management, and delivery processing. |  | 15901799607
3 | Jun YU | Technology | Technology Supervisor | Responsible for new product development and process document preparation |  | 18816906186
4 | Quanhui Zhang | Production | Production Supervisor | Responsible for the quality and system management of the product in the trial production stage, responsible for the management and maintenance of the equipment |  | 15921346433
5 | Wuhang Wang | Quality Control | Quality Supervisor | Responsible for the normal operation of the system and system management |  | 18816906186
6 | Jing Wang | Administration | Executive Assistant | Responsible for organizing staff training (new project development) |  | 15921307243
Project leader: |  | Lei zhou |  | Technology |  | 2022-05-10